## Instructions
UI Requirements, Feedback and Suggestions Template
Use this workbook to capture, prioritize and track user interface inputs for an application.
How to use this template
1 | Capture requirements | Use the Requirements sheet to document user needs, acceptance criteria, ownership and decision status.
2 | Log feedback | Use the Feedback sheet to record comments, usability findings, defects, concerns and observations from users or stakeholders.
3 | Track suggestions | Use the Suggestions sheet to record improvement ideas and prioritize them using impact and effort.
4 | Map UI scope | Use the UI Inventory sheet to list screens, pages and modules so requirements can be tied back to UI areas.
5 | Review summary | Use the Summary sheet to view counts by status, priority, severity and UI area.
Conventions
• | Blue text fields are intended for user input.
• | Black formula fields are calculated automatically.
• | Dropdown values can be edited on the hidden Lists sheet if your project needs different categories.
• | Use IDs such as REQ-001, FB-001 and SUG-001 to link related items across sheets.

## Summary
Summary Dashboard
Automated counts based on entries in the Requirements, Feedback and Suggestions sheets.
Total Requirements |  | Open Feedback |  | Approved Requirements | Completed Items
154 |  | 0 |  | 0 | 0
Requirements by Status |  |  | Requirements by Priority |  | UI Area Activity
Status | Count |  | Priority | Count | UI Area | Count
New | 0 |  | Critical | 0 | Navigation | 1
Under Review | 0 |  | High | 0 | Dashboard | 14
Approved | 0 |  | Medium | 8 | Forms/Input | 36
In Progress | 0 |  | Low | 0 | Search/Filter | 2
Deferred | 0 |  |  |  | Workflow | 3
Rejected | 0 |  |  |  | Reports/Exports | 9
Completed | 0 |  |  |  | Notifications | 0
[5 empty] | User Profile | 0
[5 empty] | Admin | 0
Feedback by Severity |  |  | Suggestions by Status |  | Mobile/Responsive | 0
Severity | Count |  | Status | Count | Other | 9
Critical | 0 |  | New | 0
High | 10 |  | Under Review | 0
Medium | 17 |  | Approved | 0
Low | 64 |  | In Progress | 0
|  |  | Deferred | 0
|  |  | Rejected | 0
|  |  | Completed | 0

## Requirements
Requirements Log
Capture UI requirements, user stories, acceptance criteria, ownership and status.
Requirement ID | Date Captured | Requested By | User Role | UI Area | Requirement | Business Rationale | Requirement Type | Priority | Status | Acceptance Criteria | Dependencies | Owner | Target Release | Due Date | Decision / Resolution | Notes
REQ-001 | 2026-08-11 | Krishna |  | Forms/Input | Change the button name "Browse S3" in the metadata mapping form |  | Usability | Medium
REQ-002 | 2026-08-11 | Krishna |  | Forms/Input | The Protocol and Trial design form hada protocol uplaoded for study 671-6974 and the trial domains were populated. It allowed me to add another protocol amendment. when i click the "Extract TDM" the trial domains are not refreshed with the amendment |  | Data/Reporting | Medium
REQ-003 | 2026-08-24 | Gopal |  | Buttons | add domains class under TOC botton in mapping spec |  | Usability | Medium
REQ-004 | 2026-08-25 | Karthik |  | Forms/Input | Protocol/TDM - We need to add TD, TM domains |  | Data/Reporting | Medium | [6 empty] | Team will add them
REQ-005 | 2026-08-25 | Karthik |  | Forms/Input | Metadata mapping: When an ALS document is uploaded, the system reads the file. Could we add a display section, similar to the Uploaded Files list, that shows the name of the source raw metadata file? This would help trace which metadata file was used during CRF migrations and amendments. |  | Data/Reporting | Medium | [6 empty] | Team will add them | ALS name to appear
REQ-006 | 2026-08-25 | Karthik |  | Forms/Input | When we upload multiple protocols, can we have an option to select which protocol has to be used for extracting TD's |  | Data/Reporting | Medium | [6 empty] | Team will restrict to add only one version of protocol
REQ-007 | 2026-08-27 | Karthik |  | Buttons | I have mapped AEYN to SUPPAE and approved it. Can we build a feature to revert the decision ? Can we have an option to review first and then approve instead of build & approve? | [10 empty] | Will fix it
REQ-008 | 2026-08-27 | Karthik |  | Reports/Exports | When we export, the file name is "mapping_spec_a9e53f52-fa0a-4b31-a542-643c29a3ae28". Could we have it started with study number , taskname, date, version X.O |  | Data/Reporting | Medium | [7 empty] | will check
REQ-009 | 2026-08-27 | Karthik |  | Forms/Input | For unmapped variables, it says one per line. Could we have the unmapped variables pulled from Metadata mapping tab instead of manual entry. AI mapping is not working - says 0 suggestions. |  | Workflow | Medium | [7 empty] | will check
REQ-0010 | 2026-08-27 | Karthik |  | Forms/Input | When we create new study - should we say what Gilead mapping spec to use? as we will have two versions of 3.4 next year ? | [10 empty] | Will add in metadata mapping
REQ-0011 | 2026-08-27 | Karthik |  | Forms/Input | Can we have option to select datasets from ALS ? For interim analysis, we might not need all datasets to be mapped | [10 empty] | local version is already updated to fix this.
REQ-0012 | 2026-09-02 | Karthik |  | Dashboard | Currently, we are seeing all studies in the dashboard. When we deploy, will the users see all studies or their own studies ? if all studies, can we add a feature to favorite them or like my studies option ? | [10 empty] | Neel is aware of it and will check
REQ-0013 | 2026-09-02 | Karthik |  | Dashboard | Build/Domain build: Can we have a column which states "like mapping from core spec: No change allowed". Otherwise, i need to look into all rows and verify | [10 empty] | Neel will add confidence column
REQ-0014 | 2026-09-03 | Karthik |  | Dashboard | Metadata mapping + AI mapping into Metadata mapping | [10 empty] | Other function groups requested to have it as separate column
REQ-0015 | 2026-09-03 | Karthik |  | Dashboard | Mapping spec: Can we have options whether to present all domains from Core mapping spec or select domains from core mapping spec to include in the final mapping spec? When the rawplus is mapped to new LABCT, we have additional domains that can be only seen from rawplus and metdata file cannot catch it. | [10 empty] | in mapping spec, TOC column will lists all the domains and user can select
REQ-0016 | 2026-09-03 | Karthik |  | Dashboard | Mapping spec: Can we keep a feature to add custom domain based on the class? Just an enhancement. | [10 empty] | Neel will check and add it
REQ-0017 | 2026-09-03 | Karthik |  | Dashboard | Autobuild: When we add a column active Y/N, can we also add an option to select all | [10 empty] | Neel will check and add it
REQ-0018 | 2026-09-03 | Karthik |  | Dashboard | Domain build: Can we add a column like "No change allowed, mapped from Core spec", so that user will have few variables to pay attention. | [10 empty] | Neel will add confidence column
REQ-0019 | 2026-09-03 | Karthik |  | Mapping spec | same as above. | [10 empty] | Neel will add confidence column
REQ-0020
REQ-0021
REQ-0022
REQ-0023
REQ-0024
REQ-0025
REQ-0026
REQ-0027
REQ-0028
REQ-0029
REQ-0030
REQ-0031
REQ-0032
REQ-0033
REQ-0034
REQ-0035
REQ-0036
REQ-0037
REQ-0038
REQ-0039
REQ-0040
REQ-0041
REQ-0042
REQ-0043
REQ-0044
REQ-0045
REQ-0046
REQ-0047
REQ-0048
REQ-0049
REQ-0050
REQ-0051
REQ-0052
REQ-0053
REQ-0054
REQ-0055
REQ-0056
REQ-0057
REQ-0058
REQ-0059
REQ-0060
REQ-0061
REQ-0062
REQ-0063
REQ-0064
REQ-0065
REQ-0066
REQ-0067
REQ-0068
REQ-0069
REQ-0070
REQ-0071
REQ-0072
REQ-0073
REQ-0074
REQ-0075
REQ-0076
REQ-0077
REQ-0078
REQ-0079
REQ-0080
REQ-0081
REQ-0082
REQ-0083
REQ-0084
REQ-0085
REQ-0086
REQ-0087
REQ-0088
REQ-0089
REQ-0090
REQ-0091
REQ-0092
REQ-0093
REQ-0094
REQ-0095
REQ-0096
REQ-0097
REQ-0098
REQ-0099
REQ-00100
REQ-00101
REQ-00102
REQ-00103
REQ-00104
REQ-00105
REQ-00106
REQ-00107
REQ-00108
REQ-00109
REQ-00110
REQ-00111
REQ-00112
REQ-00113
REQ-00114
REQ-00115
REQ-00116
REQ-00117
REQ-00118
REQ-00119
REQ-00120
REQ-00121
REQ-00122
REQ-00123
REQ-00124
REQ-00125
REQ-00126
REQ-00127
REQ-00128
REQ-00129
REQ-00130
REQ-00131
REQ-00132
REQ-00133
REQ-00134
REQ-00135
REQ-00136
REQ-00137
REQ-00138
REQ-00139
REQ-00140
REQ-00141
REQ-00142
REQ-00143
REQ-00144
REQ-00145
REQ-00146
REQ-00147
REQ-00148
REQ-00149
REQ-00150
REQ-00151 | 2026-08-27 | Krishna |  | Forms/Input | Mapping spec: Under TOC - can we have active Y/N, so user can decide what domains has to be generated for that analysis ? | [10 empty] | local version is already updated to fix this.
REQ-00152
Note on A5: Replace sample rows with your project-specific requirements.

## Feedback
Feedback Log
Record feedback from user research, usability testing, stakeholder reviews and support channels.
Feedback ID | Date | Source / Session | User / Role | UI Area | Screen / Module | Feedback Type | Severity | Feedback Summary | Current Experience | Expected Experience | Evidence / Link | Action Needed | Owner | Status | Related Requirement ID | Resolution Notes
FB-001 | 2026-08-11 | Internal Review | Krishna | Forms/Input | Metadata mapping | Question | High | The button browse s3 has folders with names that are not meaningful to select the rawdata or ALS files for the study
FB-002
FB-003 | 2026-08-18 | Internal Review | Gopal | Other | Node Graph | Enhancement | Medium | some of the graph fields aren't showing up properly like literal is linking to studyid and Domain. we need to check all the variables for accuracy. can we put Protocol as origin for STUDYID in all the SDTM domains. Even for sequence, we should something like stuydid.
FB-004 | 2026-08-18 | Internal Review | Gopal | Other | Node Graph | Enhancement | Medium | same like above .devired is linked to SUPP variables.
FB-005 | 2026-08-18 | Internal Review | Gopal | Other | Node Graph | Enhancement | Medium | can we change the COND to CODE in the graph node for derived variables to avoid confusion.
FB-006 | 2026-08-24 | Internal Review | Gopal | Other | Metadata mapping | Issue | High | looks like administrative datasets like cov_pk, ba_pk_inv are being mapped we need to drop them.
FB-007 | 2026-08-24 | Internal Review | Gopal | Other | Metadata mapping | Issue | Medium | right now sas length has decimal value showing up. can we take out the decimal from SAS length. same for KEY SEQ column
FB-008 | 2026-08-24 | Internal Review | Gopal | Buttons | Build and output | Issue | High | Auto build should be run only after the syntnetic data be enabled in order to generate outputs right now the autobuild is showing a zero domains. check for the dependencies.
FB-009 | 2026-08-24 | Internal Review | Gopal |  | delivery package | Issue | High | right now in the data package mapping spefication is not included can we add it as output along with SAS programs for download
FB-0010 | 2026-08-24 | Internal Review | Gopal | Mapping spec | implemented SAS CODE | Issue | Medium | implemented SAS code is missing for AEACN
FB-0011 | 2026-08-24 | Internal Review | Gopal | Mapping spec | variable | Issue | Low | where this varaible SPDEVID from come in EG domains
FB-0012 | 2026-08-24 | Internal Review | Gopal | AI mapping |  | Question | Low | now I dont see any unmapped variablles in AI mapping. will they be coming up once we coonect to AI models?
FB-0013 | 2026-08-24 | Internal Review | Gopal | mapping spec | TOC | Issue | High | some domains are missing labels in the TOC sheet
FB-0014 | 2026-08-24 | Internal Review | Gopal | mapping spec | TOC | Issue | High | Drug accountability label should be changed to the latest label.
FB-0015 | 2026-08-25 | Internal Review | Karthik | Dashboard | Study Details | Usability | Low | Currently owner info is displayed as Gilead email address and it is truncated (when we create new program), overlapped on created field (when we create standalone) | [7 empty] | Neel is aware of it
FB-0016 | 2026-08-25 | Internal Review | Karthik | Navigation | Protocol/TDM | Issue | Low | Browse files option is not working, it takes back to main screen | [7 empty] | Issue is only from my end.
FB-0017 | 2026-08-25 | Internal Review | Karthik | Reports/Exports | Protocol/TDM | Issue | Low | 1) Do we need add column to trial designs ? 2) I have added some rows, YZ column and downloaded to CSV. CSV file has retained the rows but not column (YZ)
FB-0018 | 2026-08-25 | Internal Review | Karthik | Forms/Input | Protocol/TDM | Issue | Low | TA/TE elements are not in sync.
FB-0019 | 2026-08-25 | Internal Review | Karthik | Forms/Input | Protocol/TDM | Issue | Low | Order of variables in details panel is not same as left panel (Trial design variables order) | [7 empty] | Neel will fix it
FB-0020 | 2026-08-25 | Internal Review | Karthik | Forms/Input | Protocol/TDM | Issue | Low | For TV - TVSTRL, ENRL is missing. For TS - TSGRPID, TSVAL1, 2, TSVALNF, TSVALCD, TSVCDREF, TSVCDVER are missing. | [7 empty] | Neel will check and update it
FB-0021 | 2026-08-25 | Internal Review | Karthik | Forms/Input | Protocol/TDM | Issue | Low | SOA - Flow diagram is tiny to read. It is generalized and not read correctly (Has Tumor assessment when protocol doesnt have it) Have Matrix in 2 places. Flow says - flow diagram is coming soon. Flow diagram option is also present just above the assessment table. | [7 empty] | Neel is aware of it
FB-0022 | 2026-08-27 | Internal Review | Karthik | Forms/Input | Metadata mapping | Issue | Low | Metadata mapping: Could not read XLS metadata file (97-2003 excel). Gave this error - could not read metadata file: Missing optional dependency 'xlrd'. Install xlrd >= 2.0.1 for xls Excel support Use pip or conda to install xlrd. What is parquet ? | [7 empty] | will remove parquet and check for XLS format
FB-0023 | 2026-08-27 | Internal Review | Karthik | Forms/Input | Metadata mapping | Issue | Low | I uploaded ALS in XLSX format and Run mapping gave me "HTTP 500" error.
FB-0024 | 2026-08-27 | Internal Review | Kai | Programs/Protocol |  | Enhancement | Low | Shows the partial value as "GS-US-XXX", please increase the length to display the full value of the protocol #.
FB-0025 | 2026-08-27 | Internal Review | Karthik | Forms/Input | Metadata mapping | Issue | Low | STATUS: For variables that are mapped, do we need the "Mark not needed" ? If we need this option, can it ask for approval before excluding. | [7 empty] | Will work around it
FB-0026 | 2026-08-27 | Internal Review | Kai | Programs/Protocol | Protocol/TDM | Issue | Low | Element shows the general TRT value but the actual treatment value.
FB-0027 | 2026-08-27 | Internal Review | Karthik | Forms/Input | Metadata mapping | Issue | Low | The hyperlink from metadata mapping to Mapping spec, doesnt give a edit option. Incase, if we need to update the labels, origin, keyseq. For example: AEACN1, 2 label has to be updated in SUPPAE. | [7 empty] | Will check and fix it
FB-0028 | 2026-08-27 | Internal Review | Kai | Programs/Protocol | Protocol/TDM | Issue | Medium | ETCD, ELEMENT values should be identical in TA and TE domains.
FB-0029 | 2026-08-27 | Internal Review | Karthik | Forms/Input | Mapping spec | Issue | Low | I added AEYN to SUPPAE. In mapping spec, the origin is displayed as "CRF" instead of "Collected¦Investigator" and action as "SUPP" with missing XML Type, Length. | [7 empty] | Will check and fix it
FB-0030 | 2026-08-27 | Internal Review | Karthik | Forms/Input | Metadata mapping | Issue | Low | AETERM, AESER has missing method/source. While other CRF fields has "Core Spec"
FB-0031 | 2026-08-27 | Internal Review | Karthik | Forms/Input | Node Graph | Issue | Low | Node Graph: Lineage is not mapping correctly for some of the variables. EPOCH is not pointed to AESTDTC. | [7 empty] | Neel is aware of it
FB-0032 | 2026-08-27 | Internal Review | Karthik | Forms/Input | Node Graph | Issue | Low | Options like COPY, CONSTANT, SEQ, DERIVED, OTHER - when we click on COPY, it deselect records that are assigned and shows other records. Same for other options. Can we update to reflect the selected option. | [7 empty] | Neel is aware of it
FB-0033 | 2026-08-27 | Internal Review | Karthik | Forms/Input | Mapping spec | Issue | Low | Key seq, SAS length is representing value in XX.0 | [7 empty] | Neel is aware of it
FB-0034 | 2026-08-27 | Internal Review | Karthik | Buttons | Annotated CRF | Issue | Low | We have 2 sections to upload CRF | [7 empty] | Neel is aware of it
FB-0035 | 2026-08-27 | Internal Review | Karthik | Buttons | Annotated CRF | Issue | Low | I tried to upload blank CRF, it ended up as "HTTP 500" error and didnt upload the file. | [7 empty] | Connection issue.
FB-0036 | 2026-08-27 | Internal Review | Karthik | Dashboard | Reference | Concern | Low | Version: it has latest, 3.3. Instead of latest, can we specify what mapping spec is used? | [7 empty] | Neel is aware of it
FB-0037 | 2026-08-27 | Internal Review | Karthik | Dashboard | Reference | Concern | Low | Any chances of including provisional spec ? | [7 empty] | Connecting to spec store is the fix. Neel to add more options/questions before Run mapping.
FB-0038 | 2026-08-27 | Internal Review | Karthik | Other | Metadata mapping | Question | Low | Status: it has PARENT_MAPPED, what does it mean ?
FB-0039 | 2026-08-27 | Internal Review | Karthik | Other | Metadata mapping | Issue | Low | Method/Source: It has Rules, what does it mean ? Can we have the meaning of options used in Status, Method/Source | [7 empty] | Neel will add footnotes
FB-0040 | 2026-08-27 | Internal Review | Karthik | Other | Metadata mapping | Issue | Low | Historical seen: the values have "seen 9999x". | [7 empty] | Neel will check and update it. It gives the confidence that variable is mapped in previous studies.
FB-0041 | 2026-08-27 | Internal Review | Karthik | Other | Metadata mapping | Issue | Low | Suggested, Actions columns: Not sorting. | [7 empty] | Neel will remove the sorting arrows for the last 2 columns.
FB-0042 | 2026-08-28 | Internal Review | Kai | Programs/Protocol | Protocol/TDM | Issue | Medium | TABRANCH is a required variable, may we auto populate this value?
FB-0043 | 2026-08-28 | Internal Review | Kai | Programs/Protocol | Protocol/TDM | Issue | Medium | Can we update VISITNUM to be more meaningful other than chronological order?
FB-0044 | 2026-08-31 | Internal Review | Karthik | Reports/Exports | Mapping spec | Question | Low | Verify complete spec: it gives count of vars for each domain. What is the source for this count? What is C, B ? | [7 empty] | Neel will add footnotes
FB-0045 | 2026-08-31 | Internal Review | Karthik | Reports/Exports | Mapping spec | Concern | Low | Verify complete spec: When we apply or reject the changes, should the Critical, major, Minor still show the same count as previous ? | [7 empty] | Neel is aware of it and will check and update it
FB-0046 | 2026-08-31 | Internal Review | Karthik | Reports/Exports | Mapping spec | Concern | Low | Diff vs Ref spec: overall match shows -%. When does it show the percentage value ? | [7 empty] | Neel is aware of it and will check and update it. It is not wired in yet.
FB-0047 | 2026-08-31 | Internal Review | Karthik | Workflow | Data prep pipeline | Question | Medium | it doesnt list any domain, how do we determine transpose, reshape ? | [7 empty] | Section be removed
FB-0048 | 2026-08-31 | Internal Review | Karthik | Workflow | Data prep pipeline | Issue | Medium | Under stack append rows - it displays the list of ALS i have uploaded. | [7 empty] | Section be removed
FB-0049 | 2026-08-31 | Internal Review | Karthik | Workflow | Data prep pipeline | Question | Low | Do we use aggregate, date extreme options in SDTM ? | [7 empty] | Section be removed
FB-0050 | 2026-08-31 | Internal Review | Karthik | Buttons | Synthetic data | Issue | Low | Download parquet option ended in error as "This XML file does not appear to have any style information associated with it. The document tree is shown below." | [7 empty] | it is just a place holder for now
FB-0051 | 2026-08-31 | Internal Review | Karthik | Dashboard | Data visualization | Question | Low | Do we need data visualization, as we are not uploading study data ? | [7 empty] | it is placeholder for now
FB-0052 | 2026-08-31 |  | Kai | Metadata mapping | Upload Metadata | Issue | High | when uploading ALS, error message "could not read metadata file: Excel file format cannot be determined, you must specify an engine manually"
FB-0053 | 2026-08-31 |  | Kai | Metadata mapping | Browse S3 | Issue | High | error meesage "fail to parse" when selecting files to ingest
FB-0054 | 2026-08-31 |  | Kai | Dashboard | Search box | Issue | Medium | The search function does not work properly. Tested: search a SDTM variable RFSTDTC.
FB-0055 | 2026-08-31 |  | Kai | Design and Mapping | Protocol/TDM | Enhancement | Low | shared across domain sign could be put as Red, to be consistent with footnote.
FB-0056 | 2026-08-31 |  | Kai | Design and Mapping | SoA Matrix Table | Question | Low | Is the DOMAIN column intended for displaying the relative SDTM domain for the assessment?
FB-0057 | 2026-08-31 |  | Kai | Design and Mapping | SoA Flow diagram | Concern | Low | Under Matrix view, there is a "Flow diagram" button, parallel to Matrix, there is another Flow tab. Are those duplicate?
FB-0058 | 2026-08-31 |  | Kai | Dashboard | Stuides Summary | Issue | Low | Studies summary keep showing 'Loading...'
FB-0059 | 2026-08-31 |  | Karthik | Reports/Exports | Build&output/ Autobuild | Concern | Low | It lists all domains, can it display only the mapped domains ? | [7 empty] | will have mapped domains. Neel will check and update it
FB-0060 | 2026-08-31 |  | Karthik | Reports/Exports | Build&output/ Autobuild | Concern | Low | SV domain is mapped in mapping spec (SV 43%) but not build during auto build | [7 empty] | Neel will check and update it.
FB-0061 | 2026-08-31 |  | Karthik | Buttons | Build&output/ Domain Build | Issue | Low | For some variables like STUDYID, DOMAIN - can we fix the preview to show only once, currently it shows thrice ? | [7 empty] | Capped to 3
FB-0062 | 2026-08-31 |  | Karthik | Buttons | Build&output/ Domain Build | Issue | Low | in Action: When we hover on Uparrow it says Derive Earlier and Down arrow (Derive later). But, those arrows are used to move the rows up and down. | [7 empty] | Neel will explain in the user guide
FB-0063 | 2026-08-31 |  | Karthik | Buttons | Build&output/ Domain Build | Issue | Low | Preview: For RFSTDTC, i edited the logic to earliest date from ex. Preview says - "✗ No objects to concatenate". | [7 empty] | Neel will check and update it.
FB-0064 | 2026-08-31 |  | Karthik | Buttons | Build&output/ Domain Build | Issue | Low | ARM: i added custom logic and it says "✗ source dataset 'python' is not available in this build — check that a prep step named 'python' exists and produces data" | [7 empty] | Neel will check and update it.
FB-0065 | 2026-08-31 |  | Karthik | Buttons | Build&output/ Domain Build | Issue | Low | For Baseline flag - we only have one variable XXTESTCD, can we add options for other grouping variables like CAT, METHOD, SPEC | [7 empty] | Neel will check and update it.
FB-0066 | 2026-08-31 |  | Karthik | Buttons | Build&output/ Domain Build | Issue | Low | TOOLS/CODE: in SAS, for EGLOXFL, it says "code — implement derivation (see the Python program) ". | [7 empty] | Neel will check and update it.
FB-0067 | 2026-08-31 |  | Karthik | Buttons | Build&output/ Domain Build | Issue | Low | TOOLS/CODE: AI polish, didnt retain variables after EGTESTCD. | [7 empty] | Neel will check and update it.
FB-0068 | 2026-09-01 |  | Kai | Metadata Mapping | Run Mapping | Issue | Medium | When click on "Run Mapping" button, it shows HTTP 500 error with 0% mapped.
FB-0069 | 2026-09-01 |  | Karthik | Forms/Input | Synthetic data | Issue | Low | Clinical datasets are generated based on ALS. The purpose of synthetic data is to see how the mappings are working correctly when we build the datasets. SUBJID is only present in SUBID synthetic dataset and not in other datasets. If we want to see the changes, how to cross check the synthetic data vs build SDTM datasets? | [7 empty] | It will be a combination of rawdata metadata (from stride) + ALS
FB-0070 | 2026-09-01 |  | Gopal | Design and Mapping | TDM | Issue | Low | TDM domains are not mapped accurately need to work on improving this
FB-0071 | 2026-09-01 |  | Karthik | Search/Filter | Mapping spec | Issue | High | If i filter on one domain, it applies to all domains in the mapping spec. Like if i filter for mapping action=ASSIGN from VS domain, it applies to all other domains, same with Method, Conf | [7 empty] | Neel will check and update it
FB-0072 | 2026-09-01 |  | Karthik | Buttons | Build & output/Domain Build | Issue | High | For prepare data, + add step - looks like it is adding a section below, but not able to expand the section. | [7 empty] | Neel will check and update it. Add a button for filter. Take user feedback on this.
FB-0073 | 2026-09-01 |  | Karthik | Buttons | Build & output/Domain Build | Issue | Medium | Tools/Graph: This graph looks like same from mapping spec/nodal graph. Do we need at both places ? | [7 empty] | Neel will check and update it
FB-0074 | 2026-09-01 |  | Karthik | Buttons | Build & output/Domain Build | Issue | Medium | Tools/code is same as code generation side bar. | [7 empty] | Neel will remove it
FB-0075 | 2026-09-01 |  | Karthik | Buttons | Build & output/Domain Build | Issue | Medium | For DM: RFXSTDTC - i changed the source to Derived and selected earliest/latest date. We have option for date, can we add the drop down to select time variable. | [7 empty] | Neel will check and update it
FB-0076 | 2026-09-01 |  | Karthik | Buttons | Build & output/Domain Build | Issue | Medium | For DM: RFXSTDTC - the nodal graph says "date_extreme" | [7 empty] | Neel will check and update it
FB-0077 | 2026-09-01 |  | Karthik | Forms/Input | Mapping spec | Issue | Low | We have CONF column with 100, 90 % - how is it calculated ?
FB-0078 | 2026-09-01 |  | Karthik | Forms/Input | Build & output/Domain Build | Issue | Low | tools/cdisc core: It says this 🛡 CDISC CORE — DM The official CDISC CORE rules engine is not installed in this environment (needs the isolated Python 3.12 venv + offline rule cache). Use Verify / Compare to spec for conformance checks here. | [7 empty] | Neel will check about it
FB-0079 | 2026-09-01 |  | Karthik | Forms/Input | Build & output/Domain Build | Issue | Low | Tools/compare to spec: Does the build match the spec is the description for this, but the build is looking into the data and spec. | [7 empty] | Expected to have
FB-0080 | 2026-09-01 |  | Karthik | Forms/Input | Build & output/Domain Build | Issue | Low | Tools/History: it stores the previous histories and restores it. But, how do we know the changes from those histories like comparison between them, for us to trace back and decide if we need to restore or not ? | [7 empty] | For now, the expectations is to have history and in future comparisons of history can be explored.
FB-0081 | 2026-09-01 |  | Karthik | Forms/Input | Build & output/Domain Build | Question | Low | What is the difference between Save and Build&save? | [7 empty] | Neel will check and update it
FB-0082 | 2026-09-01 |  | Karthik | Forms/Input | Build & output/Domain Build | Question | Low | I assigned INVNAM as ETHNIC and ran save, build &save. this change didnt reflect in mapping spec tab. | [7 empty] | Build & save will carry the logic from mapping spec.
FB-0083 | 2026-09-01 |  | Karthik | Forms/Input | Build & output/Domain Build | Question | Low | Besides tools option, i see "25 left to review 1/26", what does this reflect ? | [7 empty] | The count reflects the tick marks that user needs to review
FB-0084 | 2026-09-01 |  | Karthik | Forms/Input | Build & output/Domain Build | Issue | Low | Programs: timestamp says " 11:27:40 PM", i have generated the program at 4:34pm PST. | [7 empty] | Will check with Kiran
FB-0085 | 2026-09-01 |  | Karthik | Forms/Input | Build & output/Domain Build | Question | Medium | What is the difference between code generation vs programs ? | [7 empty] | Neel will remove one section
FB-0086 | 2026-09-01 |  | Karthik | Forms/Input | Verification & Audit | Issue | Low | Start New Run says - 0 domains | [7 empty] | it is placeholder for now
FB-0087 | 2026-09-01 |  | Karthik | Forms/Input | Review Dashboard | Issue | Low | Has all 0 values in all sections | [7 empty] | only for cSDTM team
FB-0088 | 2026-09-01 |  | Karthik | Forms/Input | Build & output/Domain Build | Issue | Low | When i select one by one, the display starts with USUBJID. | [7 empty] | It is like a freeze column, where we can see the data for each subject
FB-0089 | 2026-09-01 |  | Karthik | Buttons | Delivery package | Issue | Low | When i clicked Delivery package - the screen went blank
FB-0090 | 2026-09-01 |  | Karthik | Reports/Exports | Build&output/ Autobuild | Question | Low | What is the score here ?
FB-0091 | 2026-09-01 |  | Karthik | Reports/Exports | Build&output/ Autobuild | Question | Low | What is the safe score for us to run Auto-build compare to domain build ?
FB-0092 | 2026-09-02 |  | Karthik | Search/Filter | Main screen | Question | Low | Do we need to have search for variables in the main screen? Its not working | [7 empty] | Neel will change description from the main page and keep it in the study page
FB-0093
FB-0094
FB-0095
FB-0096
FB-0097
FB-0098
FB-0099
FB-00100
FB-00101
FB-00102
FB-00103
FB-00104
FB-00105
FB-00106
FB-00107
FB-00108
FB-00109
FB-00110
FB-00111
FB-00112
FB-00113
FB-00114
FB-00115
FB-00116
FB-00117
FB-00118
FB-00119
FB-00120
FB-00121
FB-00122
FB-00123
FB-00124
FB-00125
FB-00126
FB-00127
FB-00128
FB-00129
FB-00130
FB-00131
FB-00132
FB-00133
FB-00134
FB-00135
FB-00136
FB-00137
FB-00138
FB-00139
FB-00140
FB-00141
FB-00142
FB-00143
FB-00144
FB-00145
FB-00146
FB-00147
FB-00148
FB-00149
FB-00150

## Suggestions
Suggestions Log
Capture improvement ideas and prioritize them using impact and effort.
Suggestion ID | Date | Suggested By | User Role / Persona | UI Area | Suggestion | Expected Benefit | Impact | Effort | Priority Score | Status | Owner | Related Requirement ID | Notes
SUG-001 | 2026-08-11 | Gopal |  |  | Can we change the view of the domains to be consistent with our SDTM mapping spec. right now when I click on domain its showing ROLE as first column.
SUG-002 | 2026-08-21 | Gopal |  |  | upload the core Virology mapping specifications
SUG-003 | 2026-08-24 | Gopal |  | Diff vs Reference Spec | DIFf vs reference spec in design mapping tab only showing the wording (Compare your mapped spec against the CDISC standard reference). can we also add GCDS standards here |  |  |  | 0
SUG-004 | 2026-08-24 | Gopal |  | AUTO BUILD | Build every SDTM domain from the mapping spec + raw source data. Can we change this to raw meta data instead? |  |  |  | 0
SUG-005 | 2026-08-24 | Gopal |  | Mapping Spec | its better to keep the implemented SAS code blank for the variables when they are dropped. |  |  |  | 0
SUG-006 | 2026-08-24 | Gopal |  | mapping spec/TOC | should we display all the SDTM domains to be consistent with our standard mapping spec instead of what just mapped for our study? |  |  |  | 0
SUG-007 | 2026-08-24 | Gopal |  | Protocol/TDM | can we change the display of variable columns in the trial domains to be consistent with our mapping specification |  |  |  | 0
SUG-008 | 2026-08-24 | Gopal |  | Protocol/TDM:schedule of activities | flow chart for schedule of activities is hard to see, can we check if can add an option to zoom in? |  |  |  | 0
SUG-009 | 2026-08-24 | Gopal |  | Protocol/TDM:schedule of activities | assesment to domains are not mapped propely to the domains |  |  |  | 0
SUG-0010 | 2026-08-25 | Karthik |  | Dashboard | When we create a new study, can we have a small description on when to create New program and Standalone
SUG-0011 | 2026-08-25 | Karthik |  | Protocol/TDM | Currently add row - adds rows to the bottom, is there any flexibility to add in between too? if we need to add any element it will be useful. |  |  |  | 0
SUG-0012 | 2026-08-25 | Karthik |  | Protocol/TDM | Extract option has TDM, SAP, TOC. Do we need SAP, TOC here ? |  |  |  | 0
SUG-0013 | 2026-08-25 | Karthik |  | Protocol/TDM | When edit mode is off- could the cell be locked? Currently, changes are disabled, but clicking on the cell still highlights it as though edit mode is active. |  |  |  | 0
SUG-0014 | 2026-08-25 | Karthik |  | Protocol/TDM | In column reference - could we also show the other attributes like Type, Codelist, CDISC core (Req, Exp, Perm) |  |  |  | 0
SUG-0015 | 2026-08-27 | Karthik |  | Mapping spec | Can we have the columns aligned with the order of columns from mapping spec. Currently, label is the 3rd column and Variable is the 12th. |  |  |  | 0
SUG-0016 | 2026-08-27 | Karthik |  | Mapping spec | For mapping rule, we have wrap/unwrap option at the end of column. It works but the width of the column doesnt change. |  |  |  | 0
SUG-0017 | 2026-08-27 | Karthik |  | Mapping spec | The double headed arrow appears (when we hover to the header) but it is not resizing the column |  |  |  | 0
SUG-0018 | 2026-08-27 | Karthik |  | Mapping spec | Is it possible to freeze a column like variable column, so we can see the corresponding columns? or add hide columns option ? |  |  |  | 0
SUG-0019 | 2026-08-27 | Karthik |  | Mapping spec | UNMAPPED option: AETERM is mapped in metadata mapping but in mapping spec it shows under unmapped. Can we keep MEDDRA terms as mapped too ? |  |  |  | 0
SUG-0020 | 2026-08-27 | Karthik |  | Metadata mapping | For unmapped variables, actions show as "route". Can we have any alternate word for it ? |  |  |  | 0
SUG-0021 | 2026-08-27 | Karthik |  | Mapping spec | TOC: Has columns for Mapped, Total. Can we add Unmapped columns count ? |  |  |  | 0
SUG-0022 | 2026-08-27 | Karthik |  | Mapping spec | AE tab: For the filter fields, can we add "Missing" as an option. So, it is easy to filter for review and make changes. |  |  |  | 0
SUG-0023 | 2026-08-31 | Karthik |  | Mapping spec | History: Mapping version history window opens at the bottom of dataset section. Could it have a pop up option ? |  |  |  | 0
SUG-0024 | 2026-08-31 | Karthik |  | Mapping spec | History: Is it possible to maintain the history by domain? Currently, all the hsitory is logged by version numbers, how do we trace the changes made for each domain ? |  |  |  | 0
SUG-0025 | 2026-08-27 | Karthik |  | Build&output/ Autobuild | For each auto-build domain, the conformance section currently displays values such as: DOMAIN value → DOMAIN = 'DM' STUDYID present & non-null → STUDYID populated USUBJID present & non-null → USUBJID populated Columns populated → XX% of columns have data Could we remove the text highlighted in red? In the current auto-build dataset, USUBJID is not included, so it appears with a red cross. Displaying the red text is misleading and may cause confusion. | [7 empty] | Neel will check about it. It is placeholder for now, can be removed later
SUG-0026 | 2026-08-27 | Karthik |  | Build&output/ Domain Build | Can we add filters for the column headers of the dataset, so we can filter for DROP and focus on others ? |  |  |  | 0
SUG-0027 | 2026-08-27 | Karthik |  | Build&output/ Domain Build | The column width of label is more, can we adjust the column widths ? |  |  |  | 0
SUG-0028 | 2026-08-27 | Karthik |  | Build&output/ Domain Build | I tried to edit the value of STUDYID, it worked for that domain and once i scroll to another domain, the value resets to its original. Do we need to have EDIT option for these variables like STUDYID, DOMAIN? |  |  |  | 0
SUG-0029 | 2026-09-03 | Karthik |  | Mapping spec | When we add another metadata file at a later stage, is it possible to integrate the previous locked mapping file and this new mapping file into the final mapping spec ? |  |  |  | 0
SUG-0030
SUG-0031
SUG-0032
SUG-0033
SUG-0034
SUG-0035
SUG-0036
SUG-0037
SUG-0038
SUG-0039
SUG-0040
SUG-0041
SUG-0042
SUG-0043
SUG-0044
SUG-0045
SUG-0046
SUG-0047
SUG-0048
SUG-0049
SUG-0050
SUG-0051
SUG-0052
SUG-0053
SUG-0054
SUG-0055
SUG-0056
SUG-0057
SUG-0058
SUG-0059
SUG-0060
SUG-0061
SUG-0062
SUG-0063
SUG-0064
SUG-0065
SUG-0066
SUG-0067
SUG-0068
SUG-0069
SUG-0070
SUG-0071
SUG-0072
SUG-0073
SUG-0074
SUG-0075
SUG-0076
SUG-0077
SUG-0078
SUG-0079
SUG-0080
SUG-0081
SUG-0082
SUG-0083
SUG-0084
SUG-0085
SUG-0086
SUG-0087
SUG-0088
SUG-0089
SUG-0090
SUG-0091
SUG-0092
SUG-0093
SUG-0094
SUG-0095
SUG-0096
SUG-0097
SUG-0098
SUG-0099
SUG-00100
SUG-00101
SUG-00102
SUG-00103
SUG-00104
SUG-00105
SUG-00106
SUG-00107
SUG-00108
SUG-00109
SUG-00110
SUG-00111
SUG-00112
SUG-00113
SUG-00114
SUG-00115
SUG-00116
SUG-00117
SUG-00118
SUG-00119
SUG-00120
SUG-00121
SUG-00122
SUG-00123
SUG-00124
SUG-00125
SUG-00126
SUG-00127
SUG-00128
SUG-00129
SUG-00130
SUG-00131
SUG-00132
SUG-00133
SUG-00134
SUG-00135
SUG-00136
SUG-00137
SUG-00138
SUG-00139
SUG-00140
SUG-00141
SUG-00142
SUG-00143
SUG-00144
SUG-00145
SUG-00146
SUG-00147
SUG-00148
SUG-00149
SUG-00150
SUG-00151

## UI Inventory
UI Inventory
Map application screens, pages and modules to requirements and open questions.
Screen ID | Application Area | Screen / Page | Primary User Roles | Key Tasks | Existing Pain Points | Open Questions | Related Requirement IDs | Related Feedback IDs
UI-001
UI-002

## Lists
Priority | Status | Requirement Type | Feedback Type | Severity | UI Area | Effort | Impact | Decision | Source
Critical | New | Functional | Issue | Critical | Navigation | High | High | Accept | User Interview
High | Under Review | Usability | Enhancement | High | Dashboard | Medium | Medium | Revise | Usability Test
Medium | Approved | Accessibility | Question | Medium | Forms/Input | Low | Low | Defer | Survey
Low | In Progress | Performance | Concern | Low | Search/Filter |  |  | Reject | Support Ticket
| Deferred | Security | Positive |  | Workflow |  |  | Needs More Info | Stakeholder Review
| Rejected | Data/Reporting | Defect |  | Reports/Exports |  |  |  | Internal Review
| Completed | Workflow | Accessibility |  | Notifications |  |  |  | Other
|  | Content/Copy | Usability |  | User Profile
|  | Other |  |  | Admin
Buttons
Other